## Phase7Plan
Phase | Task ID | Category | Severity | Action | File | Lines | Description
7 | P7-01 | Rendering | Critical | FIX | Engine\Rendering\Framebuffer.cs | 100 127 | Remove DebugLogger.Log from DrawTexture and DrawText â€” per-frame file I/O at 60fps
7 | P7-02 | Engine Lifecycle | Critical | FIX | Engine\Core\GameRoot.cs | 174-177 | Add _activeScene?.Shutdown() before subsystem shutdown in RunMainLoop exit path
7 | P7-03 | Subsystem | Critical | FIX | Engine\Systems\Gameplay\CameraSystem.cs | 150-161 | Replace hardcoded 1f/60f in ApplyFollowTarget with actual deltaSeconds parameter
7 | P7-04 | Asset Pipeline | Critical | FIX | Engine\Systems\Assets\AssetPipeline.cs | 46-61 | Add Sound and Music case handlers to LoadAll switch to prevent false failure counts
7 | P7-05 | Scene System | Critical | FIX | Engine\Scenes\SceneManager.cs | 16-66 | Remove all BREAKPOINT DebugLogger.Log calls from constructor SetScene Update and Render â€” per-frame file I/O
7 | P7-06 | Rendering | Important | REMOVE | Engine\Rendering\Framebuffer.cs | 136+ | Remove dead FramebufferCS BREAKPOINT-only class
7 | P7-07 | Rendering | Important | REMOVE | Engine\Rendering\IRenderContext.cs | 13-30 | Remove dead IRenderContextCS BREAKPOINT-only class
7 | P7-08 | Rendering | Important | REMOVE | Engine\Rendering\RenderQueue.cs | 21-45 | Remove dead RenderQueueCS BREAKPOINT-only inner class
7 | P7-09 | Rendering | Important | FIX | Engine\Rendering\TextRenderer.cs | 2026-09-23 | Remove BREAKPOINT logging from constructor and remove empty Update() method
7 | P7-10 | Subsystem | Important | FIX | Engine\Systems\Gameplay\AnimationSystem.cs | 69 121 | Remove unused _removeList field and its Clear() call in Update
7 | P7-11 | Subsystem | Important | FIX | Engine\Systems\Gameplay\ProjectileSystem.cs | 2034-09-01 | Add Initialize() and Shutdown() lifecycle methods to match subsystem standard
7 | P7-12 | Engine Lifecycle | Important | FIX | Engine\Core\GameRoot.cs | 34-36 48-50 99-101 185-209 175-177 | ProjectileSystem is not instantiated or updated in GameRoot — disconnected from the engine loop. Missing from field declaration (34-36) construction (48-50) Initialize (99-101) UpdateSubsystems (185-209) and Shutdown (175-177)
7 | P7-13 | Subsystem | Important | FIX | Engine\Systems\GameStateManager.cs | 58 65 72 80 | Replace Console.WriteLine and Debug.WriteLine calls with DebugLogger.Log
7 | P7-14 | Subsystem | Important | FIX | Engine\Systems\EventDispatcher.cs | 60 | Copy handler list to array before iterating in Publish to prevent modification during enumeration
7 | P7-15 | Scene System | Important | FIX | Engine\Scenes\IScene.cs | 2026-10-15 | Add Shutdown() method to IScene interface to align with Scene base class
7 | P7-16 | Scene System | Important | REMOVE | Engine\Scenes\SceneManager.cs | 70-86 | Remove dead SampleScene test stub class
7 | P7-17 | Data Flow | Important | FIX | Engine\Core\GameRoot.cs | 78 | Capture and log AssetPipeline.LoadAll return value instead of discarding it
7 | P7-18 | Subsystem | Important | FIX | Engine\Systems\Gameplay\PathfindingSystem.cs | 126 | Add speed > 0 validation in Register to prevent zero/negative speed edge cases
7 | P7-19 | Subsystem | Minor | FIX | Engine\Systems\GameStateManager.cs | 35 | Add sealed keyword to GameStateManager class declaration
7 | P7-20 | Subsystem | Minor | FIX | Engine\Systems\GameStateManager.cs | 39 74 | Remove stale FIX 1 and FIX 2 development comments
7 | P7-21 | Subsystem | Minor | FIX | Engine\Systems\InputRouter.cs | 35 | Add sealed keyword to InputRouter class declaration
7 | P7-22 | Namespace | Minor | FIX | Engine\Systems\GameStateManager.cs | all | Fix extra indentation level wrapping entire file content
7 | P7-23 | Namespace | Minor | FIX | Engine\Systems\InputRouter.cs | all | Fix extra indentation level wrapping entire file content
7 | P7-24 | Namespace | Minor | FIX | Engine\Systems\LoggingSystem.cs | all | Fix extra indentation level wrapping entire file content
7 | P7-25 | Namespace | Minor | FIX | Engine\Scenes\SceneManager.cs | 7 | Remove meaningless using static IScene directive
7 | P7-26 | Namespace | Minor | FIX | Engine\Systems\GameStateManager.cs | 84 | Rename parameter deltaTime to deltaSeconds for consistency with other subsystems
7 | P7-27 | Data Flow | Minor | FIX | Engine\Core\GameRoot.cs | 31 43 | Either wire _frameStats.OnFrame into RunMainLoop or remove the unused field
7 | P7-28 | Rendering | Minor | FIX | Engine\Rendering\Texture2D.cs | 19-22 | Remove BREAKPOINT logging from Texture2D constructor
7 | P7-29 | Rendering | Minor | FIX | Engine\Rendering\WindowHost.cs | 49-50 | Remove per-call DebugLogger.Log from PumpEvents
7 | P7-30 | Engine Lifecycle | Minor | FIX | Engine\Core\GameLoop.cs | 35-37 40 | Remove BREAKPOINT logging and increase iteration count or document single-frame intent